## Corrective Actions
Action ID | Source | Route | Owner | Action | Due Date | Status | Completion Evidence | Last Update
CAPA-2025-041 | DOC-017 | R001 | Atlas Logistics | Document contingency capacity for critical R001 movements. | 2025-09-30 | CLOSED | Approved contingency roster and contact list. | 2025-09-26
CAPA-2025-042 | DOC-017 | R001 | Transport Planning | Add pre-dispatch capacity confirmation for designated critical R001 shipments. | 2025-10-15 | CLOSED | Control added to operating checklist. | 2025-10-10
CAPA-2026-018 | DOC-018 / DOC-020 | R003 | Nova Transportes | Implement pre-collection vehicle-assignment confirmation for critical shipments. | 2026-06-30 | CLOSED | Carrier procedure and sample confirmation records accepted. | 2026-06-28
CAPA-2026-019 | DOC-018 / DOC-020 | R003 | Supply Chain Systems | Implement exception alert for critical shipments without confirmed carrier assignment before cutoff. | 2026-07-31 | OPEN | Pilot completed; production evidence not yet accepted. | 2026-09-15
CAPA-2026-020 | DOC-018 / DOC-020 | R003 | Procurement + Supply Chain | Review contingency contacts and emergency-carrier activation readiness. | 2026-07-15 | CLOSED | Updated contact matrix and emergency activation test recorded. | 2026-07-12

## Document Control
Field | Value
Document ID | DOC-021
Title | Corrective Action Tracker
Version | 2026
Effective Date | 2026-01-01
Status | ACTIVE
Domain | Governance / Transportation
Purpose | Track corrective actions arising from transportation incidents and committee decisions.
Corpus Note | Controlled synthetic document generated for the Enterprise Knowledge AI System evaluation corpus.